## Hárok1
date | version | tester | Test scenario | Test cases | test description | expected result | test results | test result-> ok/fail/ impossible to check | found bugs | notes
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová | 1. Login and Registration Functionality | 1.1. Create a new user | click on the button "sign in" then click on -> registry now | The registration form shoud be dilplayed | registration form was opened | ok |  |  | Poznámky bokom pre budúcu konzultáciu: Content bugs - v registračnom formulári je zbytočne aj štát aj krajina
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.2. Create a new user with a very short password | fill in a reistration form with a very short password | a short password warning is displayed, a new user is not created | warning message is not displayed | fail
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.3. Create new user with incomplete registration data | fill in incomplete data in the registration form | a warning message is displayed, a new user is not created | warning message is not displayed/the system crashes | fail | Status 500 Internal Server Errorr is displayed
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.4. check whether the specified city is located in the corresponding country in the registration formula | entering a city from a different country than we set up in the registration form | warning message that the city and state do not sit should be displayed | warning message is not displayed | fail
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.5. filling the ZIP field with incorect data | fill in incorrect zip in characters not as numbers | warning message about incorrect format of the field, not creating a user | warning message is not displayed | fail
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.6. Mutual control of fields state and country in registration form | fill in the non-correspondent name of the state and the country in the registration form | warning notification of a non-correspondent name of the state and the country | warning message is not displayed/the system crashes | fail | error 500
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.7. Checking the entered phone number | enter a longer phone number than allowed ("87769789087098-09-90-0=-0=-0=-0-0-0=9-0======80") | highlighting the phone number field and displaying the warning message "incorrect format" | warning message is not displayed/the system crashes | fail | error 500
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.8. correct completion of registration data | fill in correct data in registration form | a message about the successful creation of the user is displayed | confirmation of the creation of a new user, a confirmation e-mail, will not be displayed, a new user was created | ok / fail | a new user was created without confirmation by notification or email
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.9. Login by using the sign in button with incorrect data | click on the button "sign in" then fill in incorrect "Username" and "Password" | notification about the wrong name or password should be dislpayed | any warning or notification | ok / fail | the user was not logged in, but he does not know what happened or whether he is logged in or not
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 1.10. Login by using the sign in button with correct data | click on the button "sign in" then fill in correct "Username" and "Password" | the home page opens with the user already logged in, the sign out button and the my account button appear instead of the sign in button | the home page with sign in user was displayed and buttons sign out and my account was appeared | ok
9/14/2022 | Google Chrome 105.0.5195.127 | Radek Jurášek |  | 1.11. Login on the website with valid name and password after few days | click on "sign in" button, after that input the valid name and password | after entering the correct name and password, the user will be logged in regardless of the number of days since registration | the site does not remember the registered user | fail
9/14/2022 | Google Chrome 105.0.5195.127 | Radek Jurášek |  | 1.12. Changing the registered user's password | Click on "Sign in" button then click on "My account" . Input new password and then click on -> "Save Account Information" | confirming notification about new password saving should be displayed | the password was not changed any notification | fail
9/14/2022 | Safari 15.6 | Alena Kalinska |  | 1.13. Create same user which was previously created | Click on "Sign in" after click on -?> "Register Now!" After that fill in form and create same user which was previously created -> after that click on" Save Account Information" | Warning User name already taken by other user | warning message is not displayed/ the system crashes | fail | Status 500 Internal Server Errorr is displayed
9/16/2022 | Safari 15.6 | Alena Kalinska |  | 1.14. Verify login without Username | sign in without Username | Login fails - Warning Missing Data | warning message is not displayed | fail
9/16/2022 | Safari 15.6 | Alena Kalinska |  | 1.15. Verify login without Password | sign in without Password | Login fails - Warning Missing Data | warning message is not displayed | fail
2022-09-17 | Google Chrome 105.0.5195.127 | Dominika Šuhajdová |  | 1.16. Verification of password security | fills in the password field in the form | the password is hidden, only the balls are displayed | the password is show | fail
2022-09-17 | Google Chrome 105.0.5195.127 | Dominika Šuhajdová |  | 1.17. Set language | Set language in registraion form | in registry form set the language on japane, langugage in page change into japan language | language is not changed | fail
2022-09-17 | Google Chrome 105.0.5195.127 | Dominika Šuhajdová |  | 1.18. Set the favorite category | in registry set the favorite category | after logging in again, the favorite category will remain the same as when registering | despite changing the favorite category, it still shows fish as the favorite category | fail
2022-09-17 | Google Chrome 105.0.5195.127 | Dominika Šuhajdová |  | 1.19. Set Enable MyList | in registry set the enable MyList | after logging in again, the enable MyBanner will remain the same as when registering | MyList is still unmarked | fail
2022-09-17 | Google Chrome 105.0.5195.127 | Dominika Šuhajdová |  | 1.20. Set Enable MyBanner | in registry set the MyBanner | after logging in again, the enable MyList will remain the same as when registering | MyBanner is still unmarked | fail
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová | 2. Menu and Product Catalog | 2.2. vertikal menu | click on a specific category, check the menu of specific animals | after click on a specific category, the menu of specific animals will be open | specific caregory are displayed correctly | ok
2022-11-09 | Google Chrome 105.0.5195.102 | Dominika Šuhajdová |  | 2.3. picture menu | click on a specific category, check the menu of specific animals | after click on a specific category, the menu of specific animals will be open | specific caregory are displayed correctly | ok
9/14/2022 | Google Chrome 105.0.5195.127 | Radek Jurášek |  | 2.4. conformity of the product description with the associated image | select item in section Dogs –> Labrador Retriever Adult Male/Female | after click on selected -> the selected product with the corresponding image and price will be displayed | in dogs category items and pictures does not match ID :EST-6, EST-7, EST-8, EST-9, EST-10, EST-28, EST-22, EST=23, EST-24, EST-25, EST-26, EST-27 | fail
9/16/2022 | Safari 15.6 | Alena Kalinska |  | 2.5. Check animal data | Open concrete item | Animal is in right category with correct name and picture | agrees outside the dogs category | ok
2022-12-16 | Google chrome 105.0.5195.125 | Zita Selecka | 3. Search Functionality | 3.1. search using the search button | write the name of the animal in the search field | the corresponding item is displayed | the corresponding item will only be displayed if you enter the exact name of the animal, otherwise the system will not be able to search | ok / fail
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka | 4. Shopping cart/Ordering/Payment | 4.1. Add items to the cart | select item and click on the button "Add to Cart" | in the shoping cart should be displayed selected item with correct final price | in the shoping cart is selected item with correct final price | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.2. Add the same item to the cart while continuing to shop, the item count in the shopping cart should get incremented | select the same item and click on the button "Add to Cart" | the item count in the shopping cart shoul be incremented | the item count in the shopping cart was incremented | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.3. A user can add more items to the cart | select the same item and click on the button "Add to Cart", them select another item and click on the button "Add to Cart" | all selected items are in the cart and the amounts and total ammount are correct | all selected items are in the cart and the amounts and total ammount are correct | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.4. User can remove items from the cart | select item and click on the button "Add to Cart", then click on the button "Remove" | the item is removed from the basket | the item was removed from the cart | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.5. Proceed to checkout -> Payment and order confirmation | click on the button "Proceed to checkout" | Payment Details and Billing Address should be displayed, is possible click on the button "Continue" | Payment Details and Billing Address was displayed, is possible click on the button "Continue" | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.6. Proceed to checkout -> Possibility change Billing Address | change all fields in Billing Address -> click on the button "Continue" | order recapitulation should be displayed-> Billing Address is completly changed and Shipping Address is same as in registration | order recapitulation was displayed correctly -> Billing Address is completly changed and Shipping Address is same as in registration | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.7. Proceed to checkout -> Possibility change Shipping Address | 4.7.1. click in the field "Shipp to different address" and click on the button "Continue" | editable Shipping address form should be displayed | editable Shipping address form was displayed | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  |  | 4.7.2. change all fields in Shipping Address and click on the button "Continue" | Confirmation with changed Shipping Addres shoul be displyed, Billing Address is the same | the form was displayed correctly | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.8. Proceed to checkout -> Possibility change Billing and Shipping Address all data | 4.8.1. change all fields in Billing Address -> click on the field "Shipp to different address…"-> click on the button "Continue" | the form with Shipping address should be displayed/ fulfilled by data from registration form | the form was displayed correctly | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  |  | 4.8.2. change all fields in Shipping Address -> click on button "Continue" | order confirmation with completely changed Billing and Delivery address information should be dislpayed | an order confirmation was displayed with completely changed billing and delivery address information | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.9. User can remove all items from the cart | Add a few items to the cart, in the cart are all selected items with correct prices and total amount -> then remove all items | The cart balance becomes zero, and no items should be displayed in the cart. | Shopping cart is emty and cart balance is zero | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.10. An order price updates when a user adds/removes a new item to/from the cart | Add a few items to the cart, in the cart are all selected items with correct prices and coccert total amount-> then remove some item | The cart balance was reduced by the removed product | The cart balance was reduced by the removed product correctly | ok
| Google chrome 105.0.5195.125 | Zita Selecka |  | 4.11. Non -logged in customer and creating an order | Like a non-sign in cusstomer, add to cart some inems-> click to "Preceed to Checkout | a window will appear asking you to sign in or register | the system requires user login or registration | ok
9/16/2022 | Safari 15.6 | Alena Kalinska |  | 4.12. Verify that the user can’t add more than the available in-stock quantity of the product | Select the item and add not-standard amount of items to the cart (order 100,1000,1000 000,...items) | Warning for not-standard request / Information of availability. The system reports the lack of goods in stock | The system allows you to buy any quantity of goods without checking the warehouse | fail
9/16/2022 | Safari 15.6 | Alena Kalinska |  | 4.13 . Possibility to buy negative amount of item | Add negative amount of items to the cart | Warning for not allowed/negative quantity amount should be displayed | the system did not warn about illegal values | fail
9/16/2022 | Google chrome 105.0.5195.125 | Zita Selecka |  | 4.14. Non -logged in customer and creating an order | Like a non-sign in cusstomer, add to cart some inems-> click to "Preceed to Checkout | a window will appear asking you to sign in or register | the system requires user login or registration | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka | 5. Check Home Page behavior for returning customers | 5.1. Returnig customer with unclosed order | Add some selected items to the cart , then ->sign out/ then sign in/check shopping cart | all add items are still in the cart | all add items are still in the cart | ok
2022-12-09 | Google chrome 105.0.5195.125 | Zita Selecka |  | 5.2. Reeturnig customer, check user information | Sign out -> Sign in -> click on the button "My Account" | Correct user information and Acoount information should be displayed | Correct user information and Acoount information was displayed | ok
missing contact data
missing business conditions
processing of personal data